Reg. Policy & Implementation Science - Devices

Summary of Call #6 - 2.14.18

Attendees:

Bill Abraham (Chair)

Matt Hillebrenner (Co-Chair)

Bram Zuckerman (FDA)

Emily Zeitler (Jr. Chair, Duke)

Amrut Ambardekar (Jr. Chair, U. of Co)

Peter Carson (VAMC DC)

Chris O’Connor (Inova)

Daniel Canos (CMS)

Mona Fiuzat (Duke/FDA)

Mitch Psotka (Inova)

Dan Schaber (Medtronic)

Patrick Verta (Edwards)

Richard Jacob (Patient Representative)

Unable to Attend:

Doug Mann (Wash U)

JoAnn Lindenfeld (Vanderbilt)

Joseph Rogers (Duke)

Seth Bilazarian (Abiomed)

2 main goals and updates:

1. Lean CRF: The goal is to create a CRF that would then be signed off on by key regulators and payers (such as with the TAVR CRF).

CRF’s have been deposited in the shared drives by Medtronic, CVRx, Edwards, and Boston Scientific. Waiting to hear from Abbott and Abiomed. Bill will reach out to remind. Aim to obtain both CRM and LVAD CRF’s to be included.

Action items / next steps:

- Complete CRF depositing (goal deadline of 2/26) – Bill / others to reach out to contacts at Abiomed and Abbott

- Will take 1-2 weeks for Medtronic statistician to pull common elements

- Review first cut of data, add/subtract as needed

- Create the common core, then add elements in layers for a modular approach (HFrEF, HFpEF, Advanced HF, etc).

- Should be able to present draft or first cut by April meeting

2) Common set of endpoint definitions/ARC definitions: Bill spoke with Bob Kormos about the ARC effort underway for MCS. Will send a few representatives to ACC meeting. Their effort is focused specifically on MCS and primarily definitions of AE’s, and some efficacy endpoints. Important to align with their efforts (Dan and others with industry representatives will also talk to their counterparts for alignment).

ARC definitions for HF: Bill has spoken with Mitch Krucoff and they are supportive of holding a meeting for these efforts. Bill is working on raising funds and next steps to plan meeting. Andy Farb is the FDA representative on the ARC definitions. We will focus on efficacy and safety endpoints, and should include international committee members as well as drug development experts. Should also consider the role of international colleagues and/or regulators. May be good to create a good product for use in the U.S. then utilize contacts and industry partners to roll out to global authorities. PMDA and others are invited to the April think tank meeting; consider role of international participation in the HF collaboratory in future efforts.

ACTION ITEMS:

- Bill to work on next steps for meeting planning – fundraising + logistics

- Bill will create a draft outline of items to be defined

- Eventually a white paper to summarize recommendations

3. Introduction of Richard Jacob – in line with our interest of including patient participation for all of our efforts, Mr. Jacob (Richard) is a 9-year transplant recipient who is happy to help with our efforts. (Welcome!)

Next call: March 23 @ 9am ET

Think Tank April 5