Reg. Policy & Implementation Science - Devices

Summary of Call #8 - 6.11.18

Attendees:

Bill Abraham (Chair)

Matt Hillebrenner (Co-Chair)

Amrut Ambardekar (U. of Co)

Chris O’Connor (Inova)

Mona Fiuzat (Duke/FDA)

Peter Carson (VAMC DC)

JoAnn Lindenfeld (Vanderbilt)

Daniel Canos (CMS)

Patrick Verta (Edwards)

Richard Jacob (Patient Representative)

Ad hoc: Jeff Cerkvenik (Medtronic, statistician)

Unable to Attend:

Emily Zeitler (Duke)

Doug Mann (Wash U)

Joseph Rogers (Duke)

Mitch Psotka (Inova)

Bram Zuckerman (FDA)

Dan Schaber (Medtronic)

Seth Bilazarian (Abiomed)

Al Gianchetti (Xylocor)

2 main goals and updates:

1. Lean CRF:

Goal is to create a CRF that will be signed off by key regulators and payers (such as TAVR CRF) to create a uniform CRF module for baseline data collection and efficiency.

CRF’s were deposited by Medtronic, CVRx, Edwards, Abbott, Abiomed and Boston Scientific (8-10 CRFs).

Phase 1: baseline characteristics – data extraction complete. Next step: consensus meeting to establish data elements.

Phase 2: adverse events and endpoints – pending Phase 1.

Phase 3: Once common core established, add elements for a modular approach (HFrEF, HFpEF, Advanced HF, etc).

- Drugs group also very interested in translating to drug development CRFs.

Meeting via conference call on Monday, July 16 @ 1pm – 3pm EST for consensus core elements for Phase 1.

2) HF-ARC: common set of endpoint definitions: Bill, Mona and others had a call with the ARC board (Roxanna Mehran, Mitch Krucoff, Andy Farb, Bob Kormos, others) who are supportive and endorse our effort. We will coordinate and harmonize the 3 efforts underway (shock, LVAD, HF). We will be leading the HF-ARC effort. The LVAD effort is focused specifically on MCS and primarily definitions of AE’s, and some efficacy endpoints.  We will focus on efficacy and safety endpoints, and should include international committee members as well as drug development experts. Goal is to create a product for use in the U.S. then utilize contacts and industry partners to roll out to global authorities. We should look at endpoint committee charters, protocols and other materials to identify events to define. Current status is awaiting an ARC liaison from the board.

ACTION ITEMS/next steps:

- Once ARC liaison assigned, Bill, Mona will work on next steps for meeting planning – fundraising + logistics

- Proposal to create outline of items to be defined – ask industry sponsors to deposit on shared drives adjudication charters and other data collection tools for endpoints / event collection. Can utilize the same method of extraction as with the CRF’s (Jeff checking if feasible).

- Will work on a date Q3/4 for F2F meeting

- White paper to summarize recommendations – timeline approximately 1 year from start of meeting efforts

Next call: Monday, July 16 – CRF core elements call / meeting

Next Working group call: Thurs, Aug. 9 @ 11am ET