Reg. Policy & Implementation Science - Devices

Summary of Call #9 - 8.09.18

Attendees:

Bill Abraham (Chair)

Bram Zuckerman (FDA)

Chris O’Connor (Inova)

Mona Fiuzat (Duke)

Peter Carson (VAMC DC)

JoAnn Lindenfeld (Vanderbilt)

Daniel Canos (CMS)

Amrut Ambardekar (U. of Co)

Joseph Rogers (Duke)

Dan Schaber (Medtronic)

Seth Bilazarian (Abiomed)

Al Gianchetti (Xylocor)

Richard Jacob (Patient Representative)

Shashank Sinha (Inova)

Ad hoc: Federica Latta (Visiting Fellow, U. of Brescia)

Unable to Attend:

Emily Zeitler (Duke)

Doug Mann (Wash U)

Mitch Psotka (Inova)

Matt Hillebrenner (Co-Chair)

Patrick Verta (Edwards)

Ad hoc: Jeff Cerkvenik (Medtronic, statistician)

2 main goals and updates:

1. Lean CRF:

Goal is to create a CRF that will be signed off by key regulators and payers (such as TAVR CRF) to create a uniform CRF module for baseline data collection and efficiency.

CRF’s were deposited by Medtronic, CVRx, Edwards, Abbott, Abiomed and Boston Scientific.

Phase 1: Demographics and baseline characteristics – complete. Draft circulated.

Phase 2: Labs, medications, adverse events and endpoints – calls scheduled 8/13 and 9/11 to complete.

Phase 3: Once common core established, add elements for a modular approach (HFrEF, HFpEF, Advanced HF, etc).

Briefly reviewed by CDER (drugs division of FDA). Comments were:

- Interest in entry LVH (yes/no/unk) and Echo parameters

- Consider capturing eGRF as a continuous variable or using CKD staging system

https://kdigo.org/wp-content/uploads/2017/02/KDIGO_2012_CKD_GL.pdf

- Section 17: Ischemic Heart Disease, should we get more granular?

Will consider these for final phase v. modular entries.

- Drugs group will translate to drug development CRFs.

Phase 2 calls on Monday, Aug. 13 @ 12pm ET and Tues. 9/11 @ 11am ET

To revisit from Phase 1: collection of renal info; LVH; Sect. 17 – ischemic heart disease.

2) HF-ARC: common set of endpoint definitions: ARC board is supportive and will endorse our effort. We will coordinate and harmonize the 3 efforts underway (shock, LVAD, HF). We will be leading the HF-ARC effort. The LVAD effort is focused specifically on MCS and primarily definitions of AE’s, and some efficacy endpoints.  We will focus on efficacy and safety endpoints. Goal is to create a product for use in the U.S. then utilize contacts and industry partners to roll out to global authorities. We should look at endpoint committee charters, protocols and other materials to identify events to define. Current status is awaiting an ARC liaison from the board.

ACTION ITEMS/next steps:

- Once ARC liaison assigned, Bill, Mona will work on next steps for meeting planning – fundraising + logistics

- Proposal to create outline of items to be defined – consider deposit on shared drives adjudication charters and other data collection tools for endpoints / event collection. Can utilize the same method of extraction as with the CRF’s (Jeff checking if feasible).

- Likely January/Feb. for F2F meeting

- White paper to summarize recommendations – timeline approximately 1 year from start of meeting efforts

Next call: Monday, Aug. 13 – CRF core elements call / meeting; Tues. Sept. 11 call #2

Next Working group call: Wed. 9/12 (can finish CRF items if n